## Sheet1
Task Code | Task Name | WBS Element | WBS Description | Tier | Trade | Site Section | Equipment Tag | Line Tag | Start Date | Finish Date | Duration Days | Pct Complete | Dependencies
METRO-L6-0101 | Cast in-situ Pier Column P-14 | VIAD.01.PIER | Viaduct Substructure | L6 | Civil | Chainage 14+200 | PIER-14 |  | 2026-08-10 | 2026-08-18 | 8 | 100
METRO-L6-0102 | Cast in-situ Pier Column P-15 | VIAD.01.PIER | Viaduct Substructure | L6 | Civil | Chainage 14+250 | PIER-15 |  | 2026-08-15 | 2026-08-23 | 8 | 100
METRO-L6-0201 | Launch U-Girder Span P14-P15 | VIAD.02.GIRDER | Superstructure Erection | L6 | Civil | Span 14-15 | LG-01 |  | 2026-08-25 | 2026-09-02 | 8 | 100 | METRO-L6-0101, METRO-L6-0102
METRO-L6-0301 | Laying Ballastless Track Plinth Span 14-15 | TRACK.01.PLINTH | Track Infrastructure | L6 | Trackwork | Span 14-15 | PLN-1415 | UP-TRACK | 2026-09-03 | 2026-09-09 | 6 | 70 | METRO-L6-0201
METRO-L6-0401 | Erect OHE Traction Mast Span 14-15 | ELEC.01.OHE | Overhead Electrification | L6 | Traction Power | Span 14-15 | MAST-1415 | 25KV-OHE | 2026-09-08 | 2026-09-12 | 4 | 0 | METRO-L6-0301
METRO-L6-0501 | Install Axle Counter Detection Block B14 | SIG.01.AXLE | Signalling & Train Control | L6 | Signalling | Block B-14 | AXC-14 | CBTC-01 | 2026-09-10 | 2026-09-14 | 4 | 0 | METRO-L6-0301